## Schedule VOBS
Schedule
2011
Customer ID | WBS | Task Description | Subtask Description | Milestone / Not (Y/N) | Resource | Planned start date | Planned end date | Planned Hours | Remarks | Actual Start date | Actual end date | Actual hours | % completion | Spread Total Hours | time axis 2010-05-31 to 2011-06-13
VOView Tasks
| 1.8.1 | Project Maintain/Support | [11 empty] | 165 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Version 1 based largely on existing prototypes, API not complete.
| 1.8.2 | filter Class version 1
| 1.8.2.1 |  | Develop/Implement | N | D Hinshaw | 2010-06-02 | 2010-06-21 | 60 | Support only single sort column. | 2010-06-03 | 2010-06-24 | 63 | 100 | 60 | 2010-05-31: 17; 2010-06-07: 29; 2010-06-14: 14
| 1.8.2.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-06-21 | 2010-07-05 | 60 |  | 2010-06-24 | 2010-09-16 | 240 | 100 | 60 | 2010-06-14: 15; 2010-06-21: 29; 2010-06-28: 16
120
| 1.8.3 | renderer Class version 1
| 1.8.3.1 |  | Develop/Implement | N | D Hinshaw | 2010-09-20 | 2010-10-18 | 80 | Based on existing xslt, sub-widgets not supported. | 2010-09-16 | 2010-10-18 | 40 | 100 | 80 | 2010-09-20: 21; 2010-09-27: 21; 2010-10-04: 21; 2010-10-11: 17
| 1.8.3.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-10-18 | 2010-11-15 | 80 | [5 empty] | 80 | 2010-10-11: 4; 2010-10-18: 21; 2010-10-25: 21; 2010-11-01: 21; 2010-11-08: 13
160
| 1.8.4 | voview Class version 1
| 1.8.4.1 |  | Develop/Implement | N | D Hinshaw | 2010-11-15 | 2010-12-13 | 80 | No findRows() method |  |  |  |  | 80 | 2010-11-08: 8; 2010-11-15: 21; 2010-11-22: 21; 2010-11-29: 21; 2010-12-06: 9
| 1.8.4.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-12-13 | 2011-01-03 | 80 | [5 empty] | 80 | 2010-12-06: 12; 2010-12-13: 21; 2010-12-20: 21; 2010-12-27: 21; 2011-01-03: 5
160
| 1.8.5 | build/installation structure
| 1.8.5.1 |  | Design | N | D Hinshaw | 2011-01-03 | 2011-01-17 | 40 | [5 empty] | 40 | 2011-01-03: 16; 2011-01-10: 21; 2011-01-17: 3
| 1.8.5.2 |  | Develop/Implement | N | D Hinshaw | 2011-01-17 | 2011-01-31 | 40 | [5 empty] | 40 | 2011-01-17: 18; 2011-01-24: 21; 2011-01-31: 1
| 1.8.5.3 |  | Test/Delivery | Y | D Hinshaw | 2011-01-31 | 2011-02-14 | 40 | [5 empty] | 40 | 2011-01-31: 20; 2011-02-07: 20
120
Version 2, complete API, code rewrite where most needed.
| 1.8.6 | filter Class version 2
| 1.8.6.1 |  | Develop/Implement | N | D Hinshaw |  |  | 60 | Rethink query syntax and implementation |  |  |  |  | 0
| 1.8.6.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw |  |  | 40 | [5 empty] | 0
100
| 1.8.7 | renderer Class version 2
| 1.8.7.1 |  | Develop/Implement | N | D Hinshaw |  |  | 80 | Rewrite using jquery. |  |  |  |  | 0
| 18..7.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw |  |  | 80 | [5 empty] | 0
160
| 1.8.8 | voview Class version 2
| 1.8.8.1 |  | Develop/Implement | N | D Hinshaw |  |  | 40 | [5 empty] | 0
| 1.8.8.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw |  |  | 40 | [5 empty] | 0
80
| 1.8.9 | Incorporate voview 2 into Datascope
| 1.8.9.1 |  | Implement | Y | D Hinshaw |  |  | 60 | [5 empty] | 0
60
| 1.8.10 | Incorporate voview 2 into SimpleQuery
| 1.8.10.1 |  | Implement | Y | D Hinshaw |  |  | 60 | [5 empty] | 0
60
[15 empty] | 20 | 32 | 32 | 32 | 19 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 23 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Note on O4: JacksPC:Use this column as a working sum of the spread