## Schedule VOBS
Schedule
2011
Customer ID | WBS | Task Description | Subtask Description | Milestone / Not (Y/N) | Resource | Planned start date | Planned end date | Planned Hours | Remarks | Actual Start date | Actual end date | Actual hours | % completion | Spread Total Hours | time axis 2010-05-31 to 2011-06-13
VOView Tasks
| 1.1 | Project Maintain/Support | [11 empty] | 165 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Version 1 based largely on existing prototypes, API not complete.
| 1.2 | filter Class version 1
| 1.2.1 |  | Develop/Implement | N | D Hinshaw | 2010-06-02 | 2010-06-21 | 60 | Support only single sort column. | 2010-06-03 | 2010-06-24 | 63 |  | 60 | 2010-05-31: 17; 2010-06-07: 29; 2010-06-14: 14
| 1.2.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-06-21 | 2010-07-05 | 60 | [5 empty] | 60 | 2010-06-14: 15; 2010-06-21: 29; 2010-06-28: 16
120
| 1.3 | renderer Class version 1
| 1.3.1 |  | Develop/Implement | N | D Hinshaw | 2010-07-05 | 2010-07-26 | 80 | Based on existing xslt, sub-widgets not supported. |  |  |  |  | 80 | 2010-06-28: 13; 2010-07-05: 29; 2010-07-12: 29; 2010-07-19: 9
| 1.3.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-07-26 | 2010-08-09 | 80 | [5 empty] | 80 | 2010-07-19: 20; 2010-07-26: 29; 2010-08-02: 29; 2010-08-09: 2
160
| 1.4 | voview Class version 1
| 1.4.1 |  | Develop/Implement | N | D Hinshaw | 2010-08-09 | 2010-08-30 | 80 | No findRows() method |  |  |  |  | 80 | 2010-08-09: 27; 2010-08-16: 29; 2010-08-23: 24
| 1.4.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-08-30 | 2010-09-20 | 80 | [5 empty] | 80 | 2010-08-23: 5; 2010-08-30: 29; 2010-09-06: 29; 2010-09-13: 17
160
| 1.5 | build/installation structure
| 1.5.1 |  | Design | N | D Hinshaw | 2010-09-20 | 2010-09-27 | 40 | [5 empty] | 40 | 2010-09-13: 12; 2010-09-20: 28
| 1.5.2 |  | Develop/Implement | N | D Hinshaw | 2010-09-27 | 2010-10-11 | 40 | [5 empty] | 40 | 2010-09-20: 1; 2010-09-27: 29; 2010-10-04: 10
| 1.5.3 |  | Test/Delivery | Y | D Hinshaw | 2010-10-11 | 2010-10-18 | 40 | [5 empty] | 40 | 2010-10-04: 19; 2010-10-11: 21
120
Version 2, complete API, code rewrite where most needed.
| 1.6 | filter Class version 2
| 1.6.1 |  | Develop/Implement | N | D Hinshaw | 2010-10-18 | 2010-11-01 | 60 | Rethink query syntax and implementation |  |  |  |  | 60 | 2010-10-11: 8; 2010-10-18: 29; 2010-10-25: 23
| 1.6.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-11-01 | 2010-11-08 | 40 | [5 empty] | 40 | 2010-10-25: 6; 2010-11-01: 29; 2010-11-08: 5
100
| 1.7 | renderer Class version 2
| 1.7.1 |  | Develop/Implement | N | D Hinshaw | 2010-11-08 | 2010-11-29 | 80 | Rewrite using jquery. |  |  |  |  | 80 | 2010-11-08: 24; 2010-11-15: 29; 2010-11-22: 27
| 1.7.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-11-29 | 2010-12-20 | 80 | [5 empty] | 80 | 2010-11-22: 2; 2010-11-29: 29; 2010-12-06: 29; 2010-12-13: 20
160
| 1.8 | voview Class version 2
| 1.8.1 |  | Develop/Implement | N | D Hinshaw | 2010-12-20 | 2010-12-27 | 40 | [5 empty] | 40 | 2010-12-13: 9; 2010-12-20: 29; 2010-12-27: 2
| 1.8.2 |  | Develop Test Suite/Deliver | Y | D Hinshaw | 2010-12-27 | 2011-01-10 | 40 | [5 empty] | 40 | 2010-12-27: 27; 2011-01-03: 13
80
| 1.9 | Incorporate voview 2 into Datascope
| 1.9.1 |  | Implement | Y | D Hinshaw | 2011-01-10 | 2011-01-24 | 60 | [5 empty] | 60 | 2011-01-03: 16; 2011-01-10: 29; 2011-01-17: 15
60
| 1.10 | Incorporate voview 2 into SimpleQuery
| 1.10.1 |  | Implement | Y | D Hinshaw | 2011-01-24 | 2011-02-07 | 60 | [5 empty] | 60 | 2011-01-17: 14; 2011-01-24: 29; 2011-01-31: 17
60
[15 empty] | 20 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 20 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Note on O4: JacksPC:Use this column as a working sum of the spread